## Sheet1
Date |  | Milestone | Packages | Name | Supporting People | Progress (%) | Description | Dependency |  | Date
Start | End | [7 empty] | Approach | Start | End | Days
2025-05-01 | 2025-05-01 | Milestone 1 | Project Plan including Work Packages | Ruturaj | Shifi | 100% | -- | -- | Research Scope and Questions | 2025-05-01 | 2025-05-04 | 3
2025-05-01 | 2025-05-04 |  | Scripting, Keywords and Papers List | Vikas | Sai Nishchal, Jobin | 100% |  | -- | Literature Collection | 2025-05-01 | 2025-05-08 | 7
2025-05-04 | 2025-05-07 |  | Make Initial Presentation | Sidharth | Shifi | 100% |  | -- | Selecting and Evaluating Papers | 2025-05-09 | 2025-05-21 | 12
2025-05-01 | 2025-05-04 |  | Formulate Research Questions | Ruturaj | Everyone | 100% |  | -- | Data Extraction and Reverification | 2025-05-16 | 2025-06-18 | 28
2025-05-04 | 2025-05-04 |  | Obtain Research Paper Template from Sajad | Ruturaj | -- | 100% |  | -- | Comparative Analysis | 2025-06-19 | 2025-06-30 | 14
2025-05-04 | 2025-05-04 |  | Email the details to Sajad | Ruturaj | -- | 100% |  | -- | Gap Analysis and Future Directions | 2025-06-19 | 2025-06-30 | 14
[8 empty] | -- | Writing and Structuring the Survey | 2025-05-16 | 2025-08-10 | 63
2025-05-09 | 2025-05-17 | Milestone 2 | Read Research papers, start information gathering, filter out irrelevant ones | Everyone |  |  |  | --
2025-05-16 | 2025-05-23 |  | Write Introduction, abstract | By Poll | Shifin |  |  | --
2025-05-16 | 2025-05-23 |  | Background and Literature Review | By Poll |  |  |  | --
2025-05-16 | 2025-05-23 |  | Related Work | By Poll |  |  |  | --
2025-05-24 | 2025-05-27 |  | Compile and Submit Initial Draft | By Poll |  |  |  | --
2025-05-24 | 2025-05-28 |  | Make Presentation 2 | By Poll |  |  |  | --
--
2025-05-30 | 2025-06-18 | Milestone 3 | Complete reading all the research papers and data reverification | Everyonne |  |  |  | --
2025-06-19 | 2025-06-30 |  | Develop Detailed Methodology | By Poll |  |  |  | --
2025-06-30 | 2025-07-01 |  | Revise Paper based on feedback from Sajad | By Poll |  |  |  | --
2025-06-20 | 2025-06-27 |  | Internal Peer Review | By Poll |  |  |  | --
2025-06-27 | 2025-07-02 |  | Submission of Revised Draft | By Poll |  |  |  | --
2025-07-01 | 2025-07-03 |  | Make Presentation 3 | By Poll |  |  |  | --
--
2025-07-04 | 2025-07-11 | Milestone 4 | Final Revisions and Adjustments | By Poll |  |  |  | --
2025-07-12 | 2025-07-18 |  | Final Proofreading and Formatting | By Poll |  |  |  | --
2025-07-19 | 2025-07-22 |  | Prepare Final Presentation | By Poll |  |  |  | --
2025-07-25 | 2025-07-25 |  | Submit Final Paper | By Poll |  |  |  | --